## Sheet1
ID | Task Name | Duration | S | F | Predecessors | Resource Names
1 | MFL concept & Budget planning | 4 days
2 | MFL proposal | 1 days |  |  | 1
3 | Internal Approval (TAPMI Mgmt.) | 3 days |  |  | 2
4 | Local Authority Approval (Manipal muncipality) & reservation of Football stadium | 4 days |  |  | 3
5 | Formal Invitation to colleges | 2 days |  |  | 4
6 | Sponsorship searching | 15 days |  |  | 4
7 | Merchandising designing (kit, sweatshirts, etc.) | 2 days |  |  | 6
8 | Print & Social media content creation | 4 days |  |  | 4
9 | Social Media campaigning | 40 days |  |  | 8
10 | Print campaigning | 10 days |  |  | 8
11 | Vendor selection for merchandising and trophy | 3 days |  |  | 7
12 | Match officials & Medical staff reservation | 8 days |  |  | 4
13 | Procurement of Merchandising & trophy | 10 days |  |  | 11
14 | Purchase Football gears | 4 days |  |  | 4
15 | Registration processing | 15 days |  |  | 5
16 | Fixtures & timings | 1 day |  |  | 15
17 | MFL inagural ceremony | 0 days |  |  | 16
18 | MFL at action | 30 days |  |  | 17
19 | MFL closing ceremony | 0 days |  |  | 18
20 | Clousure reporting (including financials) to TAPMI Mgmt. | 3 days |  |  | 19
21